## 1. Product Overview
Item | Description
Product Name
Product Vision/ Purpose
Business Goals / Key Success factors
Primary Stakeholders

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | Fake News Detection Engine | US1 | As a user, I want Reddit posts to be automatically scanned so I can know if a post might be fake. | ML model to classify posts; data pipeline | Must Have | 5 | To Do | ML Engineer | Verify model labels fake/real | QA
E1 | Fake News Detection Engine | US2 | As a moderator, I want a reliability score so I can judge post trustworthiness. | Confidence scoring algorithm | Must Have | 3 | To Do | ML Engineer | Check score generation | QA
E2 | Explainable AI | US3 | As a user, I want explanations for why news is marked fake. | XAI module (LIME/SHAP) | Must Have | 5 | To Do | AI Engineer | Verify explanation text | QA
E2 | Explainable AI | US4 | As a user, I want highlighted misleading sentences. | NLP highlight system | Should Have | 4 | To Do | AI Engineer | Highlighted text appears | QA
E3 | Reddit Integration | US5 | As a system, I want to fetch posts from Reddit automatically. | Reddit API integration | Must Have | 3 | To Do | Backend Dev | API fetch success | QA
E3 | Reddit Integration | US6 | As a user, I want results displayed in UI. | Frontend dashboard | Must Have | 5 | To Do | Frontend Dev | UI loads results | QA
E4 | User Feedback Module | US7 | As a user, I want to report wrong predictions. | Feedback form & DB | Could Have | 2 | To Do | Backend Dev | Feedback stored | QA
E2
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release | Target Date | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2025-11-15 | Basic demo completed – Reddit post upload & Fake/Real detection pipeline working | None | Completed
v0.2 | 2025-11-22 | DeBERTa model fine-tuned (83% F1), dataset finalized, module skeleton created, full folder structure completed | HuggingFace, PyTorch | Completed
v0.3 | 2025-11-29 | Complete fact-checking pipeline integrated , FastAPI working, design docs + PRS generated for Gaming Domain | None | Completed
v0.4 | 2025-12-06 | Fetching API and Working on other domains | None | Planned
v0.5 | 2025-12-11 | MVP integrated — full gaming-domain pipeline connected (classifier + retriever + NLI + fusion) |  | Completed
v1.0 | 2025-12-13 | Final MVP ready — Reddit Fake News Detector for Gaming Domain fully working with UI + API + feedback | None | Completed
v1.1 | 2025-12-20 | Deployment of the bot to Reddit | Reddit API | Planned

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Team collaboration was great | Test coverage was low | Automate test pipeline in next sprint | Test Lead